## Taskimport-csv sample
TASK NAME | TASK ID | PREDECESSORS | PARENT TASK ID | PARENT TASK NAME | TASK COMMENT | TASK DESCRIPTION | TASK LIST ID | TASK LIST NAME | TASK OWNER | TAGS | CREATED BY | START DATE | DUE DATE | % COMPLETED | PRIORITY | CUSTOM STATUS | WORK HOURS PER OWNER | WORK HOURS UNIT | COMPLETED ON | MILESTONE NAME | MILESTONE START DATE | MILESTONE END DATE
Click the 'Users' icon on the left-side menu to invite people to this project. Clients can also be added to the project. | T1 | T15 SF |  |  | Comment Added | Click the 'Users' icon on the left-side menu to invite people to this project. Clients too can be added to the project. | 5 | A quick way to get started! | John | "Tag1"","Tag2" | John | 2019-08-13 | 2019-08-30 | 10 | High | Open | 10 | hrs |  | M1 | 2019-08-13 | 2019-09-24
Use 'Mail Alias for Project' to add status, tasks, forum posts, to submit bugs and upload documents. | T2 |  | T1 | Click the 'Users' icon on the left-side menu to invite people to this project. Clients can also be added to the project. | Comment Added | Use 'Mail Alias for Project' to add status, tasks, forum posts; submit bugs and upload documents. | 5 | A quick way to get started! | Peter | "Tag2" | Peter | 2019-08-13 | 2019-08-30 | 0 | Medium | Open | 20 | hrs |  | M1 | 2019-08-14 | 2019-09-25
A task can have multiple owners. | T3 |  |  |  | Comment Added | Multiple users can be owners for a task | 1 | Basics of Tasks & Milestones | Lakshminathan,Steve | "Tag3" | John |  |  |  | None | In Progress | 10 | hrs |  | M2 | 2019-08-15 | 2019-09-26
Start & End (Due) date can be provided for the tasks. | T4 |  |  |  | Comment Added | Start & End (Due) date can be provided for the tasks. | 1 | Basics of Tasks & Milestones | Dinesh | "Tag4" | John | 2019-08-13 | 2019-08-30 | 90 | Medium | In Progress | 8 | hrs/day |  | M2 | 2019-08-16 | 2019-09-27
Priority level can be set for a task. The vertical line beside the check-box displays the priority level. | T5 | T3 SS + 1d |  |  | Comment Added | Priority level can be set for a task. The vertical line to the left of check-box displays the priority level. | 2 | Basics of Tasks & Milestones | Naga | "Tag6" | John | 2019-08-14 | 2019-08-30 | 90 | High | In Progress | 8 | hrs/day |  | M2 | 2019-08-17 | 2019-09-28
What is the use of TaskList Id in import ? | T6 |  |  |  | Comment Added | What is the use of TaskList Id in import ? | 2 | Basics of Tasks & Milestones | Lakshminathan | "Tag1" | Peter | 2019-08-16 | 2019-09-20 | 90 | None | In Progress | 8 | hrs/day |  | M2 | 2019-08-18 | 2019-09-29
Attachments and Discussions can be associated with a task. The pin icon next to the check-box indicates the file association. | T7 |  | T6 | What is the use of TaskList Id in import ? | Comment Added | Attachments and Discussions can be associated with a task. The pin icon to the left of the check-box indicates the file association. | 2 | Basics of Tasks & Milestones | Badri,Shaun | "Tag2" | John | 2019-08-15 | 2019-09-20 | 80 | High | In Progress | 5 | hrs/day |  | M2 | 2019-08-19 | 2019-09-30
Click 'Import Task' option available next to 'New Task List' to import the tasks from CSV, JSON, and XLS format files. | T8 |  | T6 | What is the use of TaskList Id in import ? | Comment Added | Click the 'Import Task' option, available to the right of 'New Task List' option, to import the tasks from CSV, JSON and XLS format files | 2 | Basics of Tasks & Milestones | Shaun | "Tag3" | John | 2019-08-14 | 2019-09-20 | 30 | Low | Open | 5 | hrs |  | M2 | 2019-08-20 | 2019-10-01
Click the 'Export Task' option at the top right corner of this module to export the tasks for all the users or for a single user. | T9 |  | T6 | What is the use of TaskList Id in import ? | Comment Added | Click the 'Export Task' option at the top right corner of this module to export the tasks all the users or any one user | 2 | Basics of Tasks & Milestones | Lakshminathan | "Tag4" | John | 2019-08-13 | 2019-09-20 | 30 | None | Open | 0.5 | hrs |  | M2 | 2019-08-21 | 2019-10-02
This is a recurring task. | T10 |  |  |  | Comment Added | This task is a recurring one. | 3 | Basics of Tasks & Milestones | Lakshminathan | "Tag5" | John |  |  |  | Low | Open | 20 | %/day |  | M3 | 2019-08-22 | 2019-10-03
The "bell icon" at the end of the task name indicates that reminder option is active for this task. | T11 |  |  |  | Comment Added | The bell symbol at the end of the task name indicates that reminder option is active for this task. | 3 | Basics of Tasks & Milestones | Lakshminathan | "Tag4" | John |  |  |  | None | Open | 1 | %/day |  | M3 | 2019-08-23 | 2019-10-04
Time can be logged for a task using the timer available at the beginning of the task name. | T12 |  |  |  | Comment Added | Time can be logged for a task using the timer option available at the beginning of the task name | 3 | Basics of Tasks & Milestones | John | "Tag5" | John | 2019-08-15 | 2019-09-20 | 30 | High | Open | 1 | %/day |  | M3 | 2019-08-24 | 2019-10-05
Click the 'Reorder' option to change the order of the tasks. | T13 |  | T14 | This task is a closed one. | Comment Added | Click the 'Reorder' option just below this task to change the order of the tasks. | 3 | Basics of Tasks & Milestones | Peter | "Tag2" | John |  |  |  | None | Closed | 20 | %/day | 2019-09-24 | M3 | 2019-08-25 | 2019-10-06
This task is a closed one. | T14 |  |  |  | Comment Added | This task is a closed one. | 3 | Basics of Tasks & Milestones | John | "Tag3" | John | 2019-08-13 | 2019-08-30 |  | None | Closed | 4 | hrs/day | 2019-09-25 | M3 | 2019-08-26 | 2019-10-07
Change the percentage completion to 100 to indicate the task completion. | T15 | T14 FS |  |  | Comment Added | Change the percentage completion to 100 to mark the task as complete. | 3 | Basics of Tasks & Milestones | Peter | "Tag2" | John | 2019-08-30 | 2019-08-30 |  | None | Closed | 4 | hrs | 2019-09-26 | M3 | 2019-08-27 | 2019-10-08
Bugs, Timesheet, Pages, and Chat modules are not available in this demo project. Send a request to support at zohoprojects.com if you want to explore these features. | T16 | T12 FF, T14 |  |  | Comment Added | Bugs, Timesheet, Pages and Chat modules are not available in this demo project. Wish to explore them, send a request to support at zohoprojects dot com | 4 | Missing Modules | Peter | "Tag1" | John | 2019-08-30 | 2019-09-20 |  | None | Closed | 4 | hrs | 2019-09-25 | M4 | 2019-08-28 | 2019-10-09